## Sheet1
Progress	Description	Dates	Duration (Hours)
Concept	Determine concept for project	02/03/10 – 02/10/10	0.5
Evaluate Market	Analyze similar products and competition within the market	02/10/10 – 02/17/10	1
Define Requirements	Define requirements of product	02/10/10 – 02/17/10	1.5
Define Functionality	Define functionality of product	02/10/10 – 02/24/10	1
Define Risk Management	Define risks associated with the project and determine ways to reduce them	02/10/10 – 02/24/10	0.5
Define Schedule	Plan detailed and granular schedule for project	02/10/10 – 02/24/10	2
Define Budget	Determine itemized budget required for project	02/10/10 – 02/24/10	1
Iteration #1 (Inception)	Vision Statement and 20% of use cases defined. Vision statement, schedule, glossary, and budget delivered.	02/10/10 – 02/24/10	7.5
Define Use Cases	Define 80% of intended use cases	02/24/10 – 03/17/10	2
Create Main User Interface	Build primary user GUI using VB.Net tools	02/24/10 – 03/17/10	1
Create Chat-Based Functionality	Create networked chat-based functionality, including the CreateGame(), JoinGame(), and SendMessage() use cases	02/24/10 – 03/17/10	4
Define Work-Breakdown	Define breakdown of work on project	02/24/10 – 03/17/10	2
Iteration #2 (Elaboration)	80% of use cases defined. CreateGame, JoinGame, and SendMessage use cases implemented. Domain model diagram, deployment diagram, supplimental specification, WBS, and updated schedule delivered.	02/24/10 – 03/17/10	9
Create Board-based functionality	Create board-based functionality, including AddBoard(), AddObject(), DeleteObject(), and MoveObject()	03/17-10 – 04/07/10	8
Iteration #3 (Construction)	AddBoard, AddObject, DeleteObject, and MoveObject use cases implemented	03/17-10 – 04/07/10	8
Create Card-based functionality and user option functionality	Create Card-based functionality and user option functionality, including DrawCard(), ShuffleDeck(), and EditOptions() (partial)	04/07/10 – 04/21/10	6
Iteration #4 (Construction)	DrawCard, and ShuffleDeck start on EditOptions use cases implemented	04/07/10 – 04/21/10	6
Create Dice-based functionality and Moderator functionality	Create Dice-based functionality and Moderator functionality, including RollDice(), BanPlayer(), UnbanPlayer(), LockBoard()	04/21/10 – 04/28/10	6
Iteration #5 (Construction)	RollDice, BanPlayer, UnbanPlayer, and LockBoard use cases, refine EditOptions use case implemented. Beta version released. Sequence diagrams, static class diagram, code review, and testing documents delivered.	04/21/10 – 04/28/10	6
Final Release (Transition)	Final version released. User documentation, final test results, best practices evidence, and peer reviews delivered	04/28/10 – 05/04/10	8