## Sheet1
Progress	Description	Deadline
Iteration #1 (Inception)	Vision Statement and 20% of use cases completed	02/24/10
Iteration #2 (Elaboration)	CreateGame, JoinGame, and SendMessage use cases	03/17/10
Iteration #3 (Construction)	AddBoard, AddObject, and Delete Object use cases	03/24/10
Iteration #4 (Construction)	MoveObject, DrawCard, and ShuffleDeck start on EditOptions use cases	04/07/10
Iteration #5 (Construction)	RollDice, BanPlayer, UnbanPlayer, and LockBoard use cases, refine EditOptions use case	04/21/10
Final Release (Transition)	Final refinements, debugging, and testing as necessary	05/04/10