## Sheet1
Progress	Description	Deadline
Inception	Vision Statement and 20% of use cases completed	02/24/10
Iteration #2	CreateGame, JoinGame, and SendMessage use cases	03/17/10
Iteration #3	AddBoard, AddObject, and Delete Object use cases	03/24/10
Iteration #4	MoveObject, DrawCard, and ShuffleDeck start on EditOptions use cases	04/07/10
Iteration #5	RollDice, BanPlayer, UnbanPlayer, and LockBoard use cases, refine EditOptions use case	04/21/10
Final Release	Final refinements, debugging, and testing as necessary	05/04/10