## Sheet1
Progress	Description	Deadline
Iteration #1 (Inception)	Vision Statement and 20% of use cases defined. Vision statement, schedule, glossary, and budget delivered.	02/24/10
Iteration #2 (Elaboration)	80% of use cases defined. CreateGame, JoinGame, and SendMessage use cases implemented (6 hours). Domain model diagram, deployment diagram, supplimental specification, WBS, and updated schedule delivered (6 hours).	03/17/10
Iteration #3 (Construction)	AddBoard, AddObject, Delete Object, and MoveObject use cases implemented (8 hours).	03/24/10
Iteration #4 (Construction)	DrawCard, and ShuffleDeck start on EditOptions use cases implemented (4 hours).	04/07/10
Iteration #5 (Construction)	RollDice, BanPlayer, UnbanPlayer, and LockBoard use cases, refine EditOptions use case implemented (6 hours). Beta version released. Sequence diagrams, static class diagram, code review, and testing documents delivered (6 hours).	04/21/10
Final Release (Transition)	Final version released. User documentation, final test results, best practices evidence, and peer reviews delivered (8 hours).	05/04/10